## Open bugs and defects
Open bugs and defects
Issue ID | Description | Priority | Open date | Status | Discovered in | Link
SM6 | No confirmation message shown when deleting account | Low | 2025-01-06 | Open | Stage environment | jira.com
SM11 | No confirmation message shown when deleting customer | Low | 2025-01-25 | Open | Stage environment | jira.com
SM14 | "You are not authorize to edit this account!" redirects to delete customer page | Low | 2025-01-25 | Open | Stage environment | jira.com
SM15 | " You are not authorize to edit this account!" redirect to delete customer page | Low | 2025-01-26 | Open | Stage environment | jira.com
SM17 | Not redirecting to My Account page on clicking refresh button | Low | 2025-01-27 | Open | Stage environment | jira.com
SM19 | Pop-up for successful edit of account not shown | Medium | 2025-01-28 | Open | Stage environment | jira.com
SM20 | Norwegian characters (ÆØÅ) not shown correctly in booking confirmation email | Medium | 2025-01-29 | Open | Stage environment | jira.com
SM21 | Pop-up for "Invalid phone number" not shown correctly when registering new customer | Medium | 2025-01-30 | Open | Stage environment | jira.com
SM22 | Pop-up for "Seat selection" should enlarged | Medium | 2025-01-31 | Open | Stage environment | jira.com
SM25 | Typo in "Extra luggage booking"-confirmation email | Medium | 2025-02-01 | Open | Stage environment | jira.com
SM28 | Age can be less than 18 when creating new customer | Medium | 2025-02-02 | Open | Stage environment | jira.com
SM32 | "From-date"-field can be earlier than "To-date" in search | Medium | 2025-02-03 | Open | Stage environment | jira.com
SC5 | Contact form not shown correctly in "Safari" browser | Medium | 2025-02-04 | Open | Stage environment | jira.com
SC9 | Confirmation not given when seat is changed | Critical | 2025-02-05 | Open | Stage environment | jira.com
SC11 | Database output is shown on "My Bookings"-Page | Critical | 2025-02-06 | Open | Stage environment | jira.com
SC12 | getPremiumOptions-endpoint gives "500 Internal Server Error" | Critical | 2025-02-07 | Open | Stage environment | jira.com
SC13 | Regular user can view same data as Admin users on "Passenger details"-page | Critical | 2025-02-08 | Open | Stage environment | jira.com
SC14 | Ministatement is generated for any account that exists in database | Critical | 2025-02-09 | Open | Stage environment | jira.com
SC16 | Customized statement is generated for any account that exists in database | Critical | 2025-02-10 | Open | Stage environment | jira.com
SC18 | Pop-up wrongly displayed "No details found for this passenger" | Critical | 2025-02-11 | Open | Stage environment | jira.com
WS5 | Json format fail | Critical | 2025-02-12 | Open | Stage environment | jira.com
WS6 | Date/Time format in Service Inquiry Page is invalid | Critical | 2025-02-13 | Open | Stage environment | jira.com

## Sprint 1.4
System Test Report
Module | User Story | Number of TCs | % TCs Passed | Number of bugs/defects | Line of code (LOC)
Flight Search & Booking | As a passenger, I want to search for flights by date, destination, and number of passengers, so that I can find relevant options quickly. | 20 | 95% | 1 | 700
Flight Search & Booking | As a passenger, I want to filter flights by price, duration, airline, and stops, so that I can choose the best option for my needs. | 20 | 100% | 0 | 600
Flight Search & Booking | As a passenger, I want to view seat availability and select my preferred seat, so that I can ensure comfort during my flight. | 20 | 96% | 1 | 700
Flight Search & Booking | As a passenger, I want to see the total price (including taxes and fees) before payment, so that I can avoid unexpected costs. | 20 | 100% | 0 | 700
Flight Search & Booking | As a passenger, I want to receive a confirmation email with my e-ticket after booking, so that I have proof of my reservation. | 20 | 95% | 1 | 600
Payment & Checkout | As a user, I want to pay using multiple methods (credit card, PayPal, etc.), so that I can choose my preferred payment option. | 20 | 100% | 0 | 700
Payment & Checkout | As a user, I want to save my payment details securely for future bookings, so that checkout is faster next time. | 20 | 100% | 0 | 650
Payment & Checkout | As a user, I want to apply promo codes or loyalty points during checkout, so that I can get discounts. | 20 | 100% | 0 | 600
Account Management | As a registered user, I want to create and manage my profile, so that my details are saved for future bookings. | 35 | 82.85% | 6 | 1500
Account Management | As a registered user, I want to view my booking history and upcoming trips, so that I can track my travel plans. | 20 | 95% | 1 | 700
Account Management | As a registered user, I want to cancel or modify my booking (if allowed), so that I can adjust my travel plans if needed. | 20 | 95% | 1 | 750
Customer Support & Notifications | As a user, I want to receive real-time flight status updates (delays/cancellations), so that I can adjust my plans accordingly. | 20 | 100% | 0 | 650
Customer Support & Notifications | As a user, I want to contact customer support via chat/email/phone, so that I can resolve issues quickly. As a user, I want to contact customer support via chat/email/phone, so that I can resolve issues quickly. | 30 | 93.33% | 2 | 1100
Customer Support & Notifications | As a user, I want to enable SMS/email notifications for booking confirmations and reminders, so that I stay informed. | 20 | 100% | 0 | 550
Admin & Airline Staff | As an admin, I want to manage flight schedules and seat availability, so that the website reflects real-time updates. | 20 | 95% | 1 | 750
Admin & Airline Staff | As an admin, I want to process refunds and cancellations, so that users receive timely resolutions. | 20 | 100% | 0 | 600
Admin & Airline Staff | As an airline staff member, I want to check passenger manifests and manage check-ins, so that operations run smoothly. | 35 | 82.85% | 6 | 1500
Miscellaneous Features | As a frequent flyer, I want to earn and redeem loyalty points, so that I get benefits for repeat bookings. | 5 | 80% | 1 | 300
Miscellaneous Features | As a user, I want to add extras like baggage, meals, or travel insurance during booking, so that I can customize my trip. | 10 | 90% | 1 | 500
Miscellaneous Features | As a user, I want to compare prices across different airlines, so that I can find the best deal. | 5 | 100% | 0 | 350

## Sprint 1.3
System Test Report
Module | User Story | Number of TCs | % TCs Passed | Number of bugs/defects | Line of code (LOC)
Flight Search & Booking | As a passenger, I want to search for flights by date, destination, and number of passengers, so that I can find relevant options quickly. | 20 | 90% | 2 | 670
Flight Search & Booking | As a passenger, I want to filter flights by price, duration, airline, and stops, so that I can choose the best option for my needs. | 20 | 95% | 1 | 570
Flight Search & Booking | As a passenger, I want to view seat availability and select my preferred seat, so that I can ensure comfort during my flight. | 20 | 90% | 2 | 680
Flight Search & Booking | As a passenger, I want to see the total price (including taxes and fees) before payment, so that I can avoid unexpected costs. | 20 | 95% | 1 | 770
Flight Search & Booking | As a passenger, I want to receive a confirmation email with my e-ticket after booking, so that I have proof of my reservation. | 20 | 90% | 2 | 580
Payment & Checkout | As a user, I want to pay using multiple methods (credit card, PayPal, etc.), so that I can choose my preferred payment option. | 20 | 95% | 1 | 680
Payment & Checkout | As a user, I want to save my payment details securely for future bookings, so that checkout is faster next time. | 20 | 95% | 1 | 640
Payment & Checkout | As a user, I want to apply promo codes or loyalty points during checkout, so that I can get discounts. | 20 | 100% | 0 | 600
Account Management | As a registered user, I want to create and manage my profile, so that my details are saved for future bookings. | 35 | 80% | 7 | 1400
Account Management | As a registered user, I want to view my booking history and upcoming trips, so that I can track my travel plans. | 20 | 90% | 2 | 650
Account Management | As a registered user, I want to cancel or modify my booking (if allowed), so that I can adjust my travel plans if needed. | 20 | 95% | 1 | 700
Customer Support & Notifications | As a user, I want to receive real-time flight status updates (delays/cancellations), so that I can adjust my plans accordingly. | 20 | 100% | 0 | 650
Customer Support & Notifications | As a user, I want to contact customer support via chat/email/phone, so that I can resolve issues quickly. As a user, I want to contact customer support via chat/email/phone, so that I can resolve issues quickly. | 30 | 86.67% | 4 | 1000
Customer Support & Notifications | As a user, I want to enable SMS/email notifications for booking confirmations and reminders, so that I stay informed. | 20 | 95% | 1 | 500
Admin & Airline Staff | As an admin, I want to manage flight schedules and seat availability, so that the website reflects real-time updates. | 20 | 100% | 0 | 750
Admin & Airline Staff | As an admin, I want to process refunds and cancellations, so that users receive timely resolutions. | 20 | 95% | 1 | 580
Admin & Airline Staff | As an airline staff member, I want to check passenger manifests and manage check-ins, so that operations run smoothly. | 35 | 80% | 7 | 1450
Miscellaneous Features | As a frequent flyer, I want to earn and redeem loyalty points, so that I get benefits for repeat bookings. | 5 | 60% | 2 | 280
Miscellaneous Features | As a user, I want to add extras like baggage, meals, or travel insurance during booking, so that I can customize my trip. | 10 | 90% | 1 | 490
Miscellaneous Features | As a user, I want to compare prices across different airlines, so that I can find the best deal. | 5 | 100% | 0 | 350

## Sprint 1.2
System Test Report
Module | User Story | Number of TCs | % TCs Passed | Number of bugs/defects | Line of code (LOC)
Flight Search & Booking | As a passenger, I want to search for flights by date, destination, and number of passengers, so that I can find relevant options quickly. | 20 | 85% | 3 | 640
Flight Search & Booking | As a passenger, I want to filter flights by price, duration, airline, and stops, so that I can choose the best option for my needs. | 20 | 90% | 2 | 540
Flight Search & Booking | As a passenger, I want to view seat availability and select my preferred seat, so that I can ensure comfort during my flight. | 20 | 85% | 3 | 660
Flight Search & Booking | As a passenger, I want to see the total price (including taxes and fees) before payment, so that I can avoid unexpected costs. | 20 | 85% | 2 | 750
Flight Search & Booking | As a passenger, I want to receive a confirmation email with my e-ticket after booking, so that I have proof of my reservation. | 20 | 85% | 3 | 550
Payment & Checkout | As a user, I want to pay using multiple methods (credit card, PayPal, etc.), so that I can choose my preferred payment option. | 20 | 90% | 2 | 660
Payment & Checkout | As a user, I want to save my payment details securely for future bookings, so that checkout is faster next time. | 20 | 95% | 1 | 610
Payment & Checkout | As a user, I want to apply promo codes or loyalty points during checkout, so that I can get discounts. | 20 | 95% | 1 | 600
Account Management | As a registered user, I want to create and manage my profile, so that my details are saved for future bookings. | 35 | 71.43% | 10 | 1370
Account Management | As a registered user, I want to view my booking history and upcoming trips, so that I can track my travel plans. | 20 | 85% | 3 | 620
Account Management | As a registered user, I want to cancel or modify my booking (if allowed), so that I can adjust my travel plans if needed. | 20 | 90% | 2 | 670
Customer Support & Notifications | As a user, I want to receive real-time flight status updates (delays/cancellations), so that I can adjust my plans accordingly. | 20 | 95% | 1 | 620
Customer Support & Notifications | As a user, I want to contact customer support via chat/email/phone, so that I can resolve issues quickly. As a user, I want to contact customer support via chat/email/phone, so that I can resolve issues quickly. | 30 | 83.33% | 5 | 930
Customer Support & Notifications | As a user, I want to enable SMS/email notifications for booking confirmations and reminders, so that I stay informed. | 20 | 90% | 2 | 480
Admin & Airline Staff | As an admin, I want to manage flight schedules and seat availability, so that the website reflects real-time updates. | 20 | 85% | 3 | 700
Admin & Airline Staff | As an admin, I want to process refunds and cancellations, so that users receive timely resolutions. | 20 | 95% | 3 | 560
Admin & Airline Staff | As an airline staff member, I want to check passenger manifests and manage check-ins, so that operations run smoothly. | 35 | 74.29% | 9 | 1380
Miscellaneous Features | As a frequent flyer, I want to earn and redeem loyalty points, so that I get benefits for repeat bookings. | 5 | 40% | 3 | 275
Miscellaneous Features | As a user, I want to add extras like baggage, meals, or travel insurance during booking, so that I can customize my trip. | 10 | 70% | 3 | 470
Miscellaneous Features | As a user, I want to compare prices across different airlines, so that I can find the best deal. | 5 | 40% | 1 | 340

## Sprint 1.1
System Test Report
Module | User Story | Number of TCs | % TCs Passed | Number of bugs/defects | Line of code (LOC)
Flight Search & Booking | As a passenger, I want to search for flights by date, destination, and number of passengers, so that I can find relevant options quickly. | 20 | 70% | 6 | 615
Flight Search & Booking | As a passenger, I want to filter flights by price, duration, airline, and stops, so that I can choose the best option for my needs. | 20 | 80% | 4 | 500
Flight Search & Booking | As a passenger, I want to view seat availability and select my preferred seat, so that I can ensure comfort during my flight. | 20 | 70% | 6 | 640
Flight Search & Booking | As a passenger, I want to see the total price (including taxes and fees) before payment, so that I can avoid unexpected costs. | 20 | 70% | 4 | 700
Flight Search & Booking | As a passenger, I want to receive a confirmation email with my e-ticket after booking, so that I have proof of my reservation. | 20 | 75% | 5 | 520
Payment & Checkout | As a user, I want to pay using multiple methods (credit card, PayPal, etc.), so that I can choose my preferred payment option. | 20 | 80% | 4 | 630
Payment & Checkout | As a user, I want to save my payment details securely for future bookings, so that checkout is faster next time. | 20 | 85% | 3 | 580
Payment & Checkout | As a user, I want to apply promo codes or loyalty points during checkout, so that I can get discounts. | 20 | 80% | 4 | 680
Account Management | As a registered user, I want to create and manage my profile, so that my details are saved for future bookings. | 35 | 62.86% | 13 | 1300
Account Management | As a registered user, I want to view my booking history and upcoming trips, so that I can track my travel plans. | 20 | 75% | 5 | 600
Account Management | As a registered user, I want to cancel or modify my booking (if allowed), so that I can adjust my travel plans if needed. | 20 | 75% | 5 | 630
Customer Support & Notifications | As a user, I want to receive real-time flight status updates (delays/cancellations), so that I can adjust my plans accordingly. | 20 | 85% | 3 | 590
Customer Support & Notifications | As a user, I want to contact customer support via chat/email/phone, so that I can resolve issues quickly. As a user, I want to contact customer support via chat/email/phone, so that I can resolve issues quickly. | 30 | 76.67% | 7 | 900
Customer Support & Notifications | As a user, I want to enable SMS/email notifications for booking confirmations and reminders, so that I stay informed. | 20 | 80% | 4 | 460
Admin & Airline Staff | As an admin, I want to manage flight schedules and seat availability, so that the website reflects real-time updates. | 20 | 75% | 5 | 670
Admin & Airline Staff | As an admin, I want to process refunds and cancellations, so that users receive timely resolutions. | 20 | 75% | 5 | 540
Admin & Airline Staff | As an airline staff member, I want to check passenger manifests and manage check-ins, so that operations run smoothly. | 35 | 68.57% | 11 | 1330
Miscellaneous Features | As a frequent flyer, I want to earn and redeem loyalty points, so that I get benefits for repeat bookings. | 5 | 40% | 3 | 260
Miscellaneous Features | As a user, I want to add extras like baggage, meals, or travel insurance during booking, so that I can customize my trip. | 10 | 70% | 7 | 450
Miscellaneous Features | As a user, I want to compare prices across different airlines, so that I can find the best deal. | 5 | 40% | 3 | 325

## Sprint 1.0
System Test Report
Module | User Story | Number of TCs | % TCs Passed | Number of bugs/defects | Line of code (LOC)
Flight Search & Booking | As a passenger, I want to search for flights by date, destination, and number of passengers, so that I can find relevant options quickly. | 20 | 50% | 10 | 615
Flight Search & Booking | As a passenger, I want to filter flights by price, duration, airline, and stops, so that I can choose the best option for my needs. | 20 | 60% | 8 | 500
Flight Search & Booking | As a passenger, I want to view seat availability and select my preferred seat, so that I can ensure comfort during my flight. | 20 | 50% | 10 | 640
Flight Search & Booking | As a passenger, I want to see the total price (including taxes and fees) before payment, so that I can avoid unexpected costs. | 20 | 55% | 9 | 700
Flight Search & Booking | As a passenger, I want to receive a confirmation email with my e-ticket after booking, so that I have proof of my reservation. | 20 | 55% | 9 | 520
Payment & Checkout | As a user, I want to pay using multiple methods (credit card, PayPal, etc.), so that I can choose my preferred payment option. | 20 | 55% | 8 | 630
Payment & Checkout | As a user, I want to save my payment details securely for future bookings, so that checkout is faster next time. | 20 | 65% | 7 | 580
Payment & Checkout | As a user, I want to apply promo codes or loyalty points during checkout, so that I can get discounts. | 20 | 55% | 9 | 680
Account Management | As a registered user, I want to create and manage my profile, so that my details are saved for future bookings. | 35 | 51.43% | 17 | 1300
Account Management | As a registered user, I want to view my booking history and upcoming trips, so that I can track my travel plans. | 20 | 55% | 9 | 600
Account Management | As a registered user, I want to cancel or modify my booking (if allowed), so that I can adjust my travel plans if needed. | 20 | 55% | 9 | 630
Customer Support & Notifications | As a user, I want to receive real-time flight status updates (delays/cancellations), so that I can adjust my plans accordingly. | 20 | 60% | 8 | 590
Customer Support & Notifications | As a user, I want to contact customer support via chat/email/phone, so that I can resolve issues quickly. As a user, I want to contact customer support via chat/email/phone, so that I can resolve issues quickly. | 30 | 63.33% | 11 | 900
Customer Support & Notifications | As a user, I want to enable SMS/email notifications for booking confirmations and reminders, so that I stay informed. | 20 | 60% | 8 | 460
Admin & Airline Staff | As an admin, I want to manage flight schedules and seat availability, so that the website reflects real-time updates. | 20 | 50% | 10 | 670
Admin & Airline Staff | As an admin, I want to process refunds and cancellations, so that users receive timely resolutions. | 20 | 55% | 9 | 540
Admin & Airline Staff | As an airline staff member, I want to check passenger manifests and manage check-ins, so that operations run smoothly. | 35 | 54.29% | 16 | 1330
Miscellaneous Features | As a frequent flyer, I want to earn and redeem loyalty points, so that I get benefits for repeat bookings. | 5 | 20% | 4 | 260
Miscellaneous Features | As a user, I want to add extras like baggage, meals, or travel insurance during booking, so that I can customize my trip. | 10 | 60% | 8 | 450
Miscellaneous Features | As a user, I want to compare prices across different airlines, so that I can find the best deal. | 5 | 40% | 4 | 325